## Sheet1
Phase | Module | Description | Deliverables | Weights | Status | Start Date | Target Date
| Requirements Understanding | Understan problem statement, architecture, datasets, personas | Requirement understanding document | 5% | Not Started | 2026-06-11 | 2026-06-13
| Architecture Design | Design overall system architecture, agent flow, MCP architecture, deployment flow | Architecture document | 5% | Not Started
| Data Ingestion Pipeline | PDF ingestion, image ingestion, chunking, embedding generation, metadata creation | Working ingestion pipeline | 10% | Not Started
| Vector Database Setup | FAISS/ChromaDB indexing and enterprise knowledge base creation | Indexed knowledge base | 5% | Not Started
| Enterprise RAG Pipeline | Semantic search, hybrid retrieval, metadata filtering, citations | Working RAG chatbot | 10% | Not Started
| MCP Server Development | Build MCP server and PostgreSQL connectors | MCP Server with tools | 10% | Not Started
| MCP Tools Development | Create tools for patient history, appointments, billing, lab reports, doctors | Working structured retrieval | 5% | Not Started
| Multimodal AI Module | Prescription understanding, medical report extraction, OCR, vision-language processing | Vision processing module | 10% | Not Started
| Multi-Agent Orchestration | Planner, Retriever, MCP, Vision, Reasoning agents in LangGraph | LangGraph workflow | 15% | Not Started
| Reasoning & Response Generation | Context synthesis and grounded recommendations | Response generation module | 5% | Not Started
| Guardrails & Safety | Prompt injection detection, sensitive data protection, tool misuse prevention | Safety Layer | 10% | Not Started
| Frontend Development | Streamlit chat, uploads, history, dashboards | Working UI | 5% | Not Started
| Dockerization | Dockerfile, Docker Compose, container testing | Containerized solution | 2.5% | Not Started
| Azure Deployment | Deploy application to Azure Container Apps | Live deployment | 2.5% | Not Started
| Documentation & Demo | GitHub, technical docs, architecture docs, final demo | Final submission package | 5%